## Sprint Planning
Goal --- Reproducable method for automating the building of AWS Sagemaker environments to support building and running both training and prediction ML model processing
Approach --- create CLI scripts for each of the below user stories, where possible make CLI scripts dynamic and executable from python
Sprints --- Automate the following four ML env categories
| 1 | Creating a Build model dev env (e.g. Jupyter Notebook Instance, Tensorflow)
| 2 | EDA - Collect Data (S3) envs
| 3 | Train Model envs
| 4 | Deploy and Host Prediction Model envs
Sprint | # | User Stories | Owner | Points | In/Out Scope | Status
Creating a Build model dev env (e.g. Jupyter Notebook Instance, Tensorflow)
1 | 1 | Secret key | Chris |  | In
1 | 2 | Need script for creating VPC for network interfaces (dev, training, predicition) |  |  | In
1 | 3 | Need script to launch Sagemaker Notebook for dev | Tom |  | In
1 | 4 | Need script to install Anaconda packages (possible to include libraries for TensorFlow,etc) | Chris/Venkat |  | In | Chris -- going to document the docker steps in the google doc. My goal is everything I provide should be replicable
1 | 5 | Need script for creating docker container for custom code (e.g. python, tensorflow). Code from dev env in sprint 1 | Chris |  | In
1 | 6 | Need script for attaching ML storage volume | Tom |  | In
EDA - Collect Data (S3) envs
1 | 1 | Need script for creating url to s3 bucket for obtaining training data from many sources (can be single dynamic script for each S3 config (dev, training, prediction)) | Venkat |  | In
1 | 2 | Need script for creating mysql db storage | N/A |  | Out
1 | 3 | Need script for creating mongodb storage | N/A |  | Out
1 | 4 | Need script for creating hadoop storage | N/A |  | Out
Train Model envs
1 | 1 | Need compute instance for hosting training env (can be single dynamic script for launch EC2 instances for running envs (dev, training, prediction) | Venkat |  | In
1 | 2 | Need script for creating s3 bucket for storing training modeling output (can be single dynamic script for each S3 config (dev, training, prediction)) | Venkat |  | In
Deploy and Host Prediction Model envs
1 | 1 | Need script to generate url of s3 bucket for displaying prediction model result (can be single dynamic script for each S3 config (dev, training, prediction)) | Venkat |  | In
1 | 2 | Need script to compute instance for hosting prediction modeling env (can be single dynamic script for launch EC2 instances for running envs (dev, training, prediction) | Venkat |  | In
1 | 3 | Use Sagemaker Notebook sample code for running models (sample code must run from each of data storage options) | Tom |  | In
1 | 4 | Need script for configuring endpoint to host prediction model instance | Tom |  | In
Pricing API
1 | 1 | Need ability to obtain Cloud Pricing from an API | Blaine |  | In

## Assumptions
# | Assumptions
1 | Automation for cleaning, standardizing/normalizing and transforming the data are out of scope